## Info
Information on how to fill in the risk management table
Describe the technical and economic risk involved at project and/or partner level. Describe the provisions made to ensure that the funding has a high impact despite the high risk involved (risk management, risk and contingency plan). However, you should not limit yourself to describing the risk in terms of project management.
Both probability of occurrence and impact can be assessed quantitatively.
The probability of occurrence (POO) and the impact (IMP) are assessed qualitatively to calculate the risk value (RV). The probability of occurrence is estimated as a percentage for each risk separately. This is not always straightforward. If the probability of occurrence cannot be taken or derived from statistical/historical data (previous projects, FMEA (failure mode and effects analysis), etc.), however, the result will be a rough estimate.
Tips for assessing the probability of occurrence:
- take a look at past developments,
- use statistics (sick leave in different seasons, machine breakdowns, etc.),
- compare risks with each other.
Impact is the damage caused by the risk when it occurs. The key question here is: What is the cost of the damage?
Example 1: One of 2 production machines breaks down, resulting in a 50% reduction in production volume. This will in turn have an impact on turnover and profit – the value can be estimated.
Example 2: A computer programmer falls ill – what damage would this cause to the project? The absence of an employee will result in a delay in the project, which in turn will incur costs (= project costs because of longer project duration, potential penalty payment, etc.)
Once the impact and probability of occurrence have been assessed, the risk value can be calculated by multiplication. The risk value provides the basis for deriving appropriate measures.
RV = POO x IMP
Example: Risk A – machine breakdown
POO = 10%
IMP = EUR 100,000
This results in a risk value (RV) of EUR 10,000
Example: Risk B – illness of computer programmer
POO = 5%
IMP = EUR 10,000
This results in a risk value (RV) of EUR 500
The risk value helps you to:
- compare risks
- identify major risks
- assess risk management measures (e.g. the measure incurs costs of EUR 50,000, but reduces the risk value by only EUR 10,000 and would therefore not be reasonable, etc.).
But please note that there are also aspects such as image loss, environmental disasters or danger to life, which cannot be adequately included in the calculation. Even if these events are taken into account by assuming high damage costs and a very low probability of occurrence, this will still result in a low risk value. These risks should therefore also be duly considered when drawing up a risk assessment for your project.
End

## Risk Management Table
Risk ID | Risk | Effect | Work package | Responsible | Measures | Probability of occurrence [%] | Impact (estimated damage [€]) | Risk value [€]
1
2
n